## Sheet1
date | name | Task
07-07-203 | Aparna | cosmetic ecommerce : This website will be about the global brand selling personal care and beauty products, including cosmetic skin care,fragrances,nail color,body care etc . Will also describes best sellers and newly launched products.
2023-07-14 | Aparna | Read the document abpout project,dicussed about the structure and content
2023-07-14 | reshma | setup the wireframe
2023-07-15 | aneeta | Found the logo and banner,got the tagline
2023-07-18 | reshma | gathered and searched the images
2023-07-21 | Aneeta | Started the webpage related to the category of makeup
| Aparna | Started the home page
| Reshma | Started the webpage realated to catalog, which includes the products and descriptions
2023-07-22 | Aparna | login Page completed
| Reshma | Home page almost completed minor changes are there
| Aneeta | Continuing designing the Makeup screen page
2023-07-28 | Aparna | will start the cart page
| Reshma | will start the contact page. Need to Integrate maps and form.
| Aneeta | Will start the dialog box
2023-07-30 | Aparna | Design the cart page using column, display flex and integrated the table also
'' | Reshma | Completed the ContactUs page.Integrated the map and contact form in Contact us page .
2023-07-31 | Aneeta | Designing the css for makeup using flex, position,transition on each section
2023-08-01 | Aparna | Styling done for the cart page, made it responsive using media query, completed the cart page
2023-08-02 | Reshma | Created the AboutUs page. Added Images and description.
'' | Aneeta | Applied the responsive design using grid, added animation
2023-08-03 | Aparna | Made the about page using image tag and made it responsive
'' | Reshma | Integrated various webpages pages and worked on the footer navigations and social media icons
2023-08-04 | Aparna | Change the color of the footer, header, altered the about us page by making the image small and styling
'' | Reshma | Modifing the shop tile in home page.
'' | Aneeta | Added button for product description, image hyperlinks, completed the responsive design
2023-08-05 | Aparna | Checked the responsiveness of the website and made changes. Fixed bugs related to the same.
| Reshma | Integrated the changes and did the bug fixes related to the changes.
| Aneeta | Integrated the code and did the bug fixing.